## Slide 1
DEI PLAN JOURNEY AT OCC
NOVEMBER 2020
APRIL 2021
MAY 2021
TASK FORCE CREATED
    President's Taskforce on Equity and Inclusion was created to focus on diversity, equity, and inclusion
    Task Force included student, faculty, classified, and manager representatives
    DEI website was created
DEI FRAMEWORK
    Task Force will develop a formal DEI Plan framework
    This framework will include a “living” glossary of terms relevant to the plan
NOVEMBER 2021
DECEMBER 2021
FEB-MARCH 2022
MARCH 2022
APRIL 2022
SHARED NORMS DEFINED
    Task Forced defined and endorsed shared norms/ guidelines in which the group is going to operate
VISIONING SESSIONS
    Visioning sessions for the Educational Master Plan and DEI plan were held across campus
KEYS AREAS OF FOCUS
    Task Force developed key area of focus and aligned these areas with the Educational Master Plan
ACTION PLAN AREAS
    Task Force worked in groups to review information from visioning sessions and areas of focus
    These groups then drafted actions plan to be incorporated into the DEI Plan
DRAFT DEI PLAN
    Initial DEI Plan will be drafted
REVIEW & REVISE
    Draft plan will be reviewed and revised based on final HEDS survey & focus group results
    Plan will be aligned with Educational Master Plan and District DEI Plan
VET WITH CONSTITUENTS
    Final DEI Plan will be distributed and vetted with campus constituents
DEI PLAN
    Final DEI Plan is adopted
Tentative as of November 5, 2021